# Workback Schedule

5+ weeks before (Feb. to March 3):

- Confirm venue

- Get website live

- Start posting on social media (Facebook)

- Create sponsorship packages

4 weeks before (March 4 to 10):

- Figure out how to collect funds

- Continue to post on social media (Facebook)

3 weeks before (March 11 to 17):

- Create emergency response plan

- Sign venue contract

- Continue to post on social media (Facebook)

2 weeks before (March 18 to 24):

- Pay venue 25% deposit

- Collect sponsors for lanes

- Continue to post on social media (Facebook)

1 week before (March 25 to 31):

- Collect prizes for raffle

- Continue to post on social media (Facebook)

3 days before (April 1 to 4):

- Create sponsor logos for display

- Register teams (ongoing)

- Finalize number of teams

- Finalize number of volunteers and their roles

- Continue to post on social media (Facebook)

One day before (March 5):

- Second last social media post (Facebook)

- Finalize prizes

- Create Reception House information board

- Finalize budget

- Create “thank you to our sponsors” board

- Finalize number of sponsors

- Have two floats ready for if guests need change

- Make sure guests are aware of “no refund” policy

Day of event (April 6):

- Set up at venue

- Set up raffle table

- Set up Reception House info table

- Discuss duties with volunteer

- Last post on social media

- Welcome guests

- Assign lanes to guests

After event:

- Pay difference for venue

- Send food receipts to Boston Pizza’s head office

- Final written report