| Project Charter |  |  |
| --- | --- | --- |
| Project Name | Bowl-for-a-Cause |  |
| Project Sponsor | Kathie Must (Reception House) |  |
| Project Managers | Leah Ross, Robelle Meereboer, Hannah Charlton, Sarah Grandy |  |
| Project Objectives | -Raise money for Reception House ($1000) -Raise awareness about Reception House and refugee issues -Gain experience in event planning, communications, and project management |  |
| Project Description | Teams of 4-8 will bowl for a couple of hours at Bingemans Kingpin Bowlounge and purchase tickets to win raffle prizes |  |
| Target Date | April 6, 2018 |  |
| Budget | - No starting budget -Spend as little as possible |  |
| Milestone |  | Date |
| Secure venue (Bingemans) |  | deposit paid March 27, 2018 |
| Secure donations for raffle and lane sponsorships |  | ongoing through planning and execution phases. Last day April 6, 2018 |
| Have people register and pay |  | ongoing through planning and execution phases. Last day April 6, 2018 |
| Website up and running |  | Live on March 7, 2018 11:10am |
| Known Risks |  |  |
| Time constraints on adequately securing donations and attendees |  |  |
| Lack of resources including: money, knowledge, time, experience to make an event worthwhile for people, and good enough for the assignment |  |  |